## Sheet1
Milestone	Feature	Work items	UI effort	Integraton Efford (PD)	Test and Review code	Total effort	Plan	Actual
CD1	VLAN	Create	0	3	2	17	01/29/16	02/19/16
		Edit	0	2
		Delete	0	2
		Copy	1	0
		Poll	0	1
		Enable	0	1
		Disable	0	1
		Report for 4 tables	4	0
	IP Interface	Create	0	2	1	8		02/19/16
		Edit	0	2
		Delete	0	2
		Report for 1 table	1	0
CD2	VLAN	edit Link Aggregate	1	1		2	02/26/16	02/23/16
	IP Router	View	2	1	3	19		None
		Create	3	2
		Edit	2	2
		Delete	1	2
		Report for 1 table	1	0
	Spanning Tree	Port View	2	1	2	18		03/11/16
		Bridge View	2	1
		Edit Port	2	2
		Edit Bridge	2	2
		Report for 2 table	2	0
	MVRP	Summary View	2	1	2	15		03/11/16
		Global Configuration	2	2
		Port Configuration	3	2
		Report for 1 table	1	0