## Sheet1
Tasks	Server Side Availability	UI Availability
VLAN Integration
View VLAN
VLAN Summary	01/27/16	01/29/16
VLAN with assigned port and link aggs	01/27/16	01/29/16
Spanning Tree
Switch Info	02/19/16	1
Port	02/19/16	1
Bridge Info	02/19/16	1
Spanning Tree Updates	02/24/16	4
IP Router
IP Router View	03/08/16	1
IP Router Create and Attach to VLAN	03/16/16	4
IP Router Delete		2PDs
Report for 1 table		0.5PDs
IP Interface View
IP Interface View	01/27/16	2PDs
Create/Edit	02/12/16	2PDs
Delete	02/19/16	2PDs
VLAN Management
Create Vlan with adding members	02/08/16	3
Edit Vlan with support of updating member information	02/17/16	3
Delete Vlan	02/10/16	2PDs
Enable/Disable Vlan	02/08/16	2PDs
Report for 4 tables		2PDs